Iteration Process
Iteration n - 1
Iteration n
2 weeks long
Code Freeze
Friday 3 PM EST
Start: Wed
End: Tue
Prioritize
user stories
Wed, early,
1 hr
Prepare user stories
* writing
* user story readiness
   checklist
Review and demo
(to wider audience)
1 hr
Develop prioritized
User stories
* story done checklist
* user stories not
   Modified once work
   starts
Estimate user stories
(size / length)
Mon, Tue regularly
scheduled
Validate user stories
* story validation
   checklist
Retrospective
1 hr
User story backlog
Stored in pivotal
Everyone has read access
Backlog editors:
Steve
Dave
Josh
Kay
Workstream leaders
Development Done Checklist
Checked in
Unit tests written, passed
Integration tests written, passed
Deployed to QA
Code Freeze
Branch code from trunk
Only bug fixes on the branch
Only merge from branch to trunk
Validation Done Checklist
Internal validation (BA / tester)
Product owner validation
TODO: resolution between tester and developer