## Sheet1
ID
DE1 | Extract dictionary terms using API | <tr><td>DE1</td><td>Extract dictionary terms using API</td></tr>
DE2 | Extract assay definitions using API | <tr><td>DE2</td><td>Extract assay definitions using API</td></tr>
DE3 | extract experiments using API | <tr><td>DE3</td><td>extract experiments using API</td></tr>
DE4 | extract results using API | <tr><td>DE4</td><td>extract results using API</td></tr>
DE5 | ontology / deep validation of experiments and results and notification of issues | <tr><td>DE5</td><td>ontology / deep validation of experiments and results and notification of issues</td></tr>
DE6 | Deposit experiments and results using API (basic validation, document API) | <tr><td>DE6</td><td>Deposit experiments and results using API (basic validation, document API)</td></tr>
DE7 | Update dictionary term with load status using API | <tr><td>DE7</td><td>Update dictionary term with load status using API</td></tr>
DE8 | update assay definition with load status using API | <tr><td>DE8</td><td>update assay definition with load status using API</td></tr>
DE9 | update experiment with load status using API | <tr><td>DE9</td><td>update experiment with load status using API</td></tr>
DE10 | Show me all experiments that I've uploaded to BARD | <tr><td>DE10</td><td>Show me all experiments that I've uploaded to BARD</td></tr>
DE11 | Replace existing results using API | <tr><td>DE11</td><td>Replace existing results using API</td></tr>
DE12 | Update an experiment using API | <tr><td>DE12</td><td>Update an experiment using API</td></tr>
DE13 | Delete an experiment and its results using API | <tr><td>DE13</td><td>Delete an experiment and its results using API</td></tr>
<tr><td></td><td></td></tr>
iteration 1 |  | <tr><td>iteration 1</td><td></td></tr>
DE1 | start Extract dictionary terms using API | <tr><td>DE1</td><td>start Extract dictionary terms using API</td></tr>
<tr><td></td><td></td></tr>
iteration 2 |  | <tr><td>iteration 2</td><td></td></tr>
***DE1*** | Extract dictionary terms using API | <tr><td>***DE1***</td><td>Extract dictionary terms using API</td></tr>
DE2 | start Extract assay definitions using API | <tr><td>DE2</td><td>start Extract assay definitions using API</td></tr>
<tr><td></td><td></td></tr>
iteration 3 |  | <tr><td>iteration 3</td><td></td></tr>
***DE2*** | start Extract assay definitions using API | <tr><td>***DE2***</td><td>start Extract assay definitions using API</td></tr>
<tr><td></td><td></td></tr>
iteration 4 |  | <tr><td>iteration 4</td><td></td></tr>
***DE3*** | extract experiments using API | <tr><td>***DE3***</td><td>extract experiments using API</td></tr>
***DE4*** | extract results using API | <tr><td>***DE4***</td><td>extract results using API</td></tr>
<tr><td></td><td></td></tr>
iteration 5 |  | <tr><td>iteration 5</td><td></td></tr>
***DE5*** | ontology / deep validation of experiments and results and notification of issues | <tr><td>***DE5***</td><td>ontology / deep validation of experiments and results and notification of issues</td></tr>
<tr><td></td><td></td></tr>
iteration 6 |  | <tr><td>iteration 6</td><td></td></tr>
***DE6*** | Deposit experiments and results using API (basic validation, document API) | <tr><td>***DE6***</td><td>Deposit experiments and results using API (basic validation, document API)</td></tr>
<tr><td></td><td></td></tr>
iteration 7 |  | <tr><td>iteration 7</td><td></td></tr>
| TBD or buffer | <tr><td></td><td>TBD or buffer</td></tr>
<tr><td></td><td></td></tr>
iteration 8 |  | <tr><td>iteration 8</td><td></td></tr>
| testing | <tr><td></td><td>testing</td></tr>