## Sheet1
Month | Iteration
June | 1 | Move AID to experiment level | Name and ID and AID | Basic Info (descriptions Plus clobs) | Manually load 10 probe-related assays | Load experiment info
| 2 | other external assay cross reference info | assign assay formats | assign assay types | Refine plan based on data loaded to date
July | 3 | assign targets | extract and parse measures / result types | assign projects using pubchem summary AIDs
| 4 | align and assign measures / result types | load results
August | 5 | load 'easy' result contexts | text extraction of cells and cell lines
| 6 | align and assign cells and cell lines | text extraction of assay components
Sept. | 7 | align and assign assay components | de-duplicate / merge assays
| 8 | Review & spot check data | Run validation rules engine to flag valid and invalid assays | Select data for presentation
Oct. |  | Focus on adding missing assay components and other attributes
Nov. |  | Focus on adding missing result contexts
Dec. |  | Clean up terms from external sources (GO, ATCC, etc.) | General data review and clean up
Jan. |  | Select data for presentation
|  |  |  | Difficulty | Effort
|  |  | Move AID to experiment level | 1
|  |  | Name and ID and AID | 1
|  |  | Basic Info (descriptions Plus clobs) | 2
|  |  | other external assay cross reference info | 2
|  |  | context items | 4 |  | depends on terms in ontology
|  |  | measures | 3 |  | depends on terms in ontology
|  |  | experiments | 2
|  |  | projects | 3
|  |  | results | 5
|  |  | result contexts | 4
|  |  | de-duplicate / merge assays | 4
|  |  | Visual review by biologists | 3 | 5
As a biologist, I want to group together context items
align extracted terms with ontology (GATE)
assign targets
Assay / Experiment Validation Rules Engine